## Slide 1
Role
Approval
Y
Business Development
Opportunity assessment
Business Case
Business Plan
Final Business Plan
Stage of Project
Opportunity scanning
R&D
Business Enquiries
Assess opportunity and market needs
Develop alternatives
Assess risks and uncertainties
Seek alignment with strategy
Select best alternative
Develop engineering design criteria
Select technology
Develop business
Define scope
Project execution plan
Supply and offtake agreements
Concept
Pre-Feasibility
Feasibility
Detailed Engineering
Engineering Study
Preliminary engineering proposals
Capital estimate: > +/-50%
Pre-feasibility study
Study estimate +/-30%
Feasibility study
Budget estimate +/-15%
Detailed engineering package
Control estimate +/-10%
Y
Y
Y
Strategic fit
Accept next phase plan
Right business
Preliminary financials
Accept next phase plan
Right solution
Financials
Accept next phase plan
Project authorization
Accept implementation plan

## Slide 2
DIRECT COST
INDIRECT COST
EQUIPMENT
CONSTRUCTION
Major Equipment
Bulk Material
Freight & Transportation
Site Facilities
Site Costs
Civil
Mechanical
Electrical
Instrumentation
Commissioning
Detailed Engineering
Procurement Services
Management
Construction Team Camp
Fees
ENGINEERING
PROCUREMENT
CONSTRUCTION
MANAGEMENT
OWNER’S COST
Order of Magnitude Studies
Basic Engineering
CONTINGENCY
Allowances

## Slide 3
0
1
2
3
4
5
6
0
10
20
30
40
50
Level of accuracy (% plus or minus)
Cost of estimate as % of total project cost

## Slide 4
+100%
+50%
+30%
+15%
-50%
-30%
-10%
-5%
Lower limit of accuracy estimate
Upper limit of accuracy estimate
Confidence limit
Current Estimate
Concept
Pre-Feasibility
Feasibility
Detailed Engineering

## Slide 5
Raw Materials
Operating Labour
Supervision
Utilities
Maintenance and Repairs
Supplies
Analysis
Licence Fees & Royalties
MANUFACTURING COST
GENERAL COST
DIRECT PRODUCTION
Safety, Health and Environment
Storage
Packaging
Fire Department
Maintenance and Workshops
ADMINISTRATIVE
SALES AND DISTRIBUTION
Management Salaries
Administrative Wages
Offices
Sales and Support
Shipping
Advertising
FIXED
PLANT OVERHEAD
Insurance
Rent
TOTAL OPERATING COST